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SSC JS Work Plan, 2026-2030

Members reviewed and endorsed the SSC JS work plan for 2026-2030. The Work Plan will be submitted to the SC for review.


[image: ][image: ]North Pacific Fisheries Commission


  2nd Floor Hakuyo Hall, 
Tokyo University of Marine Science and Technology,
4-5-7 Konan, Minato-ku, Tokyo
108-8477, JAPAN
TEL	+81-3-5479-8717
FAX	+81-3-5479-8718
Email	secretariat@npfc.int
Web	www.npfc.int

16
FIVE-YEAR WORK PLAN
Small Scientific Committee on Japanese Sardine (SSC JS)

Priority list:
1. Data preparation and review of biological information
2. Conduct stock assessment of Japanese sardine
3. Set biological reference points
4. Provide scientific advice on the management of Japanese sardine stock to the Commission
5. Explore the influence of climate changes on Japanese sardine stock
6. Regularly update and refine inputs

	ITEM
	2026
	2027
	2028
	2029
	2030
	Progress

	Regular update of inputs
	
	
	
	
	
	

	Research survey indices

	Submit standardized fishery-independent indices
	Update
	Update
	Update
	Update
	

	CPUE indices

	Submit standardized CPUE
	Update
	Update
	Update
	Update
	

	Catch data/catch composition

	Provide catch composition data
	Update
	Update
	Update
	Update
	

	Biological parameters (maturity, M, weight)
	Review biological parameters
	Review biological parameters
	Review biological parameters
	Review biological parameters
	Review biological parameters
	

	Fishery data (CAA, WAA, Maturity-at-age)
	Provide fishery data
	Update
	Update
	Update
	Update
	

	Stock assessment
	
	
	
	
	
	

	Benchmark stock assessment

	
	Conduct provisional stock assessment
	Update SA 
	Update SA 
	Update SA 
	

	Improvement and further investigation of the selected model
	
	
	Review and improve, if needed, the SA model
	Review and improve, if needed, the SA model
	Review and improve, if needed, the SA model
	

	Reference points, HCR, future projections and MSE
	
	
	
	
	
	

	Set biological reference points (limit and target)
	
	Provide candidate reference points
	Review and calculate reference points
	Review and calculate reference points
	Review and calculate reference points
	

	Develop future projections
	
	Provide future projections, if possible
	Same as on the left
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