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SSC NFS intersessional activities and timelines for the 2026 operational year

	Activity/Task
	Deadline
	Responsibility and Reference/Comment

	Members

	Data sharing
	See Data call
	· Members operating NFS fisheries and/or conducting research surveys
· Collaboration site / SC database

	Updates on Members' fishery status and research activities up to 2026
	May 7
(two weeks prior SSC NFS05)

	· Members operating NFS fisheries and/or conducting research surveys
· IP (ppt slides)
· See template for fisheries status information for NFS

	Updates of biological information for NFS
	Same as above

	· If available
· WP or IP

	Common sampling protocol for collecting NFS age and size data
	Same as above

	· If available
· WP

	Standardized fishery-dependent and fishery-independent abundance indices up to 2026
	Same as above

	· Members operating NFS fisheries and/or conducting research surveys
· WP
· See CPUE Standardization Protocol for NFS

	Stock assessment modelling results
	Same as above

	· If available
· WP
· See Stock Assessment Protocol for NFS

	Research on climate change impacts on NFS
	Same as above

	· If available
· WP or IP

	Members' sampling programs for transshipped catch, subject to discussion at SC11
	Same as above

	· Members doing transshipments of NFS
· WP or IP

	Fisheries-dependent indicators: 
a. Standardized CPUE (see above)
b. Cohort-specific mean size at catch, if available
c. Total catch (eAR)
	Same as above

	· Members operating NFS fisheries
· WP

	Fisheries-independent indicators: a. Abundance index from surveys conducted by China and Japan up to 2025
b. Size composition from surveys conducted by China and Japan up to 2025
	Same as above

	· China, Japan
· WP

	Chair/Secretariat/Invited expert

	Data call
	Aug 2026
	Secretariat
Post the updated data call on the website https://www.npfc.int/sc-data-call

	Invited expert’s roles and tasks for the 2026 operational year (annexed to SSC NFS04 report)
	Same as above
	Secretariat/Chair
Deliver to invited expert, draft/update a consultancy agreement

	Annotated Indicative Schedule
	May 7
(two weeks prior SSC NFS05)
	Secretariat

	Work Plan of the SSC NFS 
	Same as above

	Chair/Secretariat
Update up to 2031


	Species summary for neon flying squid update
	Same as above

	Chair/Secretariat
Include 2026 data


	Updated joint CPUE standardization up to 2026
	Same as above

	Invited expert

	Science-based options for operationalizing precautionary approach
	Same as above

	Chair/Secretariat in consultation with SC Chair and Members
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