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NPFC-2026-SSC NFS04-WP01 (Rev. 1)
Five-Year Work Plan of the SSC NFS

Abstract: The Five-Year Work Plan of the SSC NFS was updated by the Chair. Members reviewed the work plan during the SSC NFS04 meeting and recommendeded it to the SC. 

Priority list:
1. Continue research to appropriately separate two cohorts using spatial and age/size characteristics
2. Continue CPUE standardization work 
3. Continue research and literature reviews to better understand the biological characteristic (e.g., growth rate, natural mortality), life history (e.g., cohorts associated with spawning timing and location, feeding and spawning migration) of the species and population structure (e.g. genetic analysis)
4. Conduct a stock assessment based on surplus production model
5. Further investigate improvements to the surplus production model
6. Explore and develop alternative approaches, such as the management strategy evaluation framework and data-limited management procedures, to provide effective management advice
7. Conduct research and literature reviews to better understand the factors driving abundance fluctuations (including climate change) in this short-lived species
8. Develop other models e.g., age/size-structured model
9. Develop databases to support age/size-structured models


	ITEM
	2026
	2027
	2028
	2029
	2030
	Progress

	Regular update of inputs
	
	
	
	
	
	

	Update & improvement of CPUE indices
	Submit standardized CPUE by each member 
	Update
	Update
	Update
	Update
	Updated CPUE indices of Japanese survey and Chinese, Japanese and Chinese Taipei’s squid fisheries.

	Joint CPUE standardization 
	Conduct joint CPUE standardization
	Update
	Update
	Update
	Update
	Invited expert updated joint CPUE standardization and R package was shared with Members.

	Regular update of surplus production model
	
	
	
	
	
	

	Update and review of surplus production model and other stock assessment models
	Conduct preliminary stock assessment using standardized CPUE from each member
	Conduct benchmark stock assessment
	Update
	Update
	Update
	China and Japan conducted preliminary stock assessment using JABBA and SPiCT, respectively.

	Improvement and further investigation of surplus production model
	Review any outcomes of improvements, inter alia in light of possible incorporation of environmental information
	Same as on the left
	Same as on the left
	Same as on the left
	Same as on the left
	No progress 

	NFS biology 
	
	
	
	
	
	

	Data inventory (CPUE and size/age in space and time from research surveys)
	
	Conditional age at length information.
Spatio-temporal variation of size composition. 
	TBD
	TBD
	TBD
	Information on size composition was shared by some Members

	Summarizing available information on neon flying squid biology
	
	Update regularly, specifically maturity ogive, growth function by cohort, W-L relationship and its variability.
Conduct research and literature reviews to better understand the factors driving abundance fluctuations
	Continue
	Continue
	Continue
	Updated information on spawning ground and age composition 

	Toward other approaches to provide management advises 
	
	
	
	
	
	

	MSE or data-limited management procedures
	Explore methods and tools for MSE
	Explore methods and tools for MSE
	TBD
	TBD
	TBD
	Pew presented simulation methods for the assessment and MSE for short-lived species

	Review other successful (or unsuccessful) stock assessment and management practices for squid or other short-lived species globally to inform SSC NFS work

	No planned task 
	No planned task
	TBD
	TBD
	TBD
	Invited expert reviewed stock assessment methods and management measures for squid and other short-lived species



  TEL	+81-3-5479-8717
FAX	+81-3-5479-8718
Email	secretariat@npfc.int
Web	www.npfc.int
2nd Floor Hakuyo Hall, 
Tokyo University of Marine Science and Technology,
4-5-7 Konan, Minato-ku, Tokyo
108-8477, JAPAN

6
image1.wmf

image2.png




image3.png




