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TWG CMSA intersessional activities and timelines for the 2026 operational year

TWG CMSA12 (data preparatory meeting), 4-6 November 2026
	Activity/Task
	Deadline
	Responsibility and Reference/Comment

	Members

	Data sharing for stock assessment update
	See Data call
(one month before TWG CMSA12)
	· Members operating CM fisheries and/or conducting research surveys
· Collaboration site [SC database]

	Submission of data for COM10 Task 1
	Oct 4
(one month before TWG CMSA12)
CM data sharing for COM09&10 tasking
	· All Members operating CM fisheries
· Gear-specific catch-at-age / catch-at-length data for the 2025/2026 fishing season for both the Convention Area and EEZs
· Information on accessory devices used for fishing purposes
· See the Chair’s letter on Task 1 data submission
· See COM10 Paragraph 83

	Updates on Members' fishery status and research activities up to 2026
	Oct 21
(two weeks prior TWG CMSA12)
	· Members operating CM fisheries and/or conducting research surveys
· IP (ppt slides)


	Updates of biological information for CM
	Same as above

	· If available
· WP or IP

	Documents on standardized fishery-dependent and fishery-independent abundance indices up to 2026
	Same as above

	· Members operating CM fisheries and/or conducting research surveys
· WP
· See CPUE Standardization Protocol for CM

	Stock assessment updates, if available
	Same as above

	· If available
· WP
· See Stock Assessment Protocol for CM

	Chair/Secretariat/Invited expert

	Data call update
	Nov 2026
	Secretariat
Post the updated data call on the website https://www.npfc.int/sc-data-call

	Table of intersessional activities and timelines update
	Same as above
	Secretariat/Chair
Annex the table to TWG CMSA12 meeting summary




TWG CMSA13 (stock assessment meeting), 11-14 January 2027
	Activity/Task
	Deadline
	Responsibility and Reference/Comment

	Members

	Data sharing
	See Data call
	· Members operating CM fisheries and/or conducting research surveys
· Collaboration site [SC database]

	Stock assessment modelling results
	Dec 29
(two weeks prior TWG CMSA13)
	· If available
· WP
· See Stock Assessment Protocol for CM

	Research on climate change impacts on CM
	Same as above

	· If available
· WP or IP

	Members' sampling programs for transshipped catch, if applicable
	Same as above

	· Members doing transshipments of CM
· WP or IP

	Updates on Members' fishery status and research activities up to 2026, if possible
	Same as above

	· Members operating CM fisheries and/or conducting research surveys
· IP (ppt slides)

	Chair/Secretariat/Invited expert

	Annotated Indicative Schedule
	Dec 29
(two weeks prior TWG CMSA13)
	Secretariat

	Work Plan of the TWG CMSA
	Same as above

	Chair/Secretariat.
Update up to 2031


	Species summary for chub mackerel update
	Same as above

	Chair/Secretariat.
Include 2026 data


	Data call update
	Jan 2027
	Secretariat.
Post the updated data call on the website https://www.npfc.int/sc-data-call

	Invited expert’s roles and tasks for the 2027 operational year
	Same as above
	Secretariat/Chair.
Deliver to invited expert, draft/update a consultancy agreement.
Annex to TWG CMSA13 report)

	Table of intersessional activities and timelines update
	Same as above
	Secretariat/Chair.
Annex the table to TWG CMSA13 report
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